Methodology for Enterprise Restructuring

By Bert van Manen

Companies pass through different phases in their lifetime. Good times are followed by bad times, expansion is followed by retraction. Sometimes, companies cannot ensure their continuity and are partly or entirely liquidated. Through their life cycle, companies from time to time need to be restructured, dramatically changing course to restore profitable operations. Restructuring is a change in company strategy without which its continuity could not be ensured. Restructuring is often forced by impending bankruptcy. It also naturally follows on divestiture or privatisation.

# I 	The Restructuring Process

The methodology of enterprise restructuring is based on a strategic planning process. This consists of three phases:

1	Diagnostic phase - Diagnosis of the company through ‘strategic appraisal’ (± four months)

2	Planning phase - Preparation of the ‘strategic improvement plan’ (business plan, ± two months)

- Implementation phase - Restructuring, including monitoring of progress and revisions of the previous phases (± eighteen months)

The process and methodology of diagnostic review and strategic planning is summarised in the figure below. The diagnostic phase analyses the internal and external environment of the company, its relative position on the market, and its position relative to the competition. Thus, in-depth studies are conducted into the operations of the company, in particular its marketing, production, organisation and finance functions, problems encountered, their causes and possible solutions. The local and export market is extensively investigated, as is the competition. Based on this information, the SWOT analysis is completed: the relative strengths & weaknesses (internal), and the opportunities & threats in the external environment. Through this analysis, the company’s competitive advantages on the market can be determined.

With a thorough and detailed diagnostic, the development of the restructuring plan is not very difficult. Based on the SWOT, the corporate objectives, mission statement and subsequently corporate and business unit strategies are developed - strategic planning. Having completed this important step, the corresponding objectives and actions at the functional level (marketing, production, organisation, and finance) logically follow. Accordingly, financial projections (scenario’s) are developed, as is an action plan clearly outlining what is to be done to implement the restructuring plan, when and by whom. This process is further clarified in the three chapters that follow.

# II 	The Company Diagnostic

The company diagnostic, or the ‘strategic appraisal’ of the enterprise, consists of five consecutive steps. This leads to a diagnostic report by the fourth month of project implementation. Apart from technical studies, the diagnostic phase includes a number of participatory planning sessions with middle and higher management staff, aiming to uncover strategic bottlenecks for the company’s development, assessing the options, and defining new strategic directions.

1. 	Identification of stakeholders in the company - who will be affected. These are the management, shareholders, workers (some of whom may be shareholders as well), clients, suppliers, distributors, creditors, banks, government, and others. Are they willing to collaborate in the restructuring exercise? Are there any conflicting interests among the stakeholders?

2. 	Pre-assessment of the current situation. What are the present product / market combinations. How has the company performed in recent years? What would be the outcome of a strategy ‘continue business as usual’? Would the company be able to secure its continuity without restructuring?

3. 	Internal analysis aims at identification of strengths and weaknesses in the company’s structure, culture, and resources. The internal analysis includes a review of sales, costs, profits, organisational structure, management style, technology, financial results, and other factors. For the main functional areas of marketing, production, organisation and finance diagnostic tables are made, demonstrating the problems found, their consequences, and possible solutions (see example). The internal analysis also identifies Strategic Business Units (SBUs) that could be operated independently from the rest of the enterprise. Core businesses and core competencies are identified, that is SBUs that are considered crucial to the company’s existence and survival. Determine the competitive strengths and weaknesses of SBUs, starting with the ‘core businesses’.

4.	External analysis of the economic environment, markets and competition. This implies a critical analysis of elements / developments outside the company that are (potentially) relevant to the performance of the company, and most of which can not be directly influenced by the company. This includes an assessment of macro economic, legal and political developments in the country, market analysis (prospective product / market combinations), customers, competitors, distribution channels, logistics, and the environment.

5. 	SWOT-analysis at the strategic level: relative strengths & weaknesses, opportunities & threats. This helps the enterprise identify its competitive advantages on the market. Competitive advantages may be found at the level of manufacturing (enabling a company to produce a product cheaper), product design and / or quality (enabling a company to reach higher levels of customer satisfaction), marketing (enabling the company to exploit market opportunities), distribution (aiming to better reach the client), and many others.

The SWOT summarises the findings from the diagnostic, and places this information in a strategic framework for company improvement. Through the SWOT we match strengths with opportunities (take advantage), aim to convert weaknesses into strengths (improve), and determine how threats can be avoided by specific actions (upgrade). Thus, the SWOT helps determine what the company already does well, how it can use these skills to grab opportunities, and where it needs to make improvements to counter threats and overcome weaknesses. The SWOT, which is the outcome of the diagnostic study, is an extremely important step in establishing the priorities for the restructuring plan. In fact, having completed the diagnostic tables and SWOT the outline for the restructuring plan is already on the table…

# III 	The Restructuring Plan

The ‘strategic planning’ process consists of another four steps (step six to nine), during which concrete restructuring actions are formulated. Step ten aims to put in place a framework to monitor to what extent the restructuring plan is being implemented and its goals are being realised (‘strategy implementation’).

6. 	Strategic planning - define global objectives. Based on the SWOT, the enterprise’s objectives, its strategic vision and business philosophy is formulated. What do we want to achieve in terms of profit, market penetration, client satisfaction, and other objectives at the corporate level. Which business are we in, or do we want to be in, and in which we no longer operate. Define a new mission statement, showing what the company is, what it stands for, and what it does for others. Strategic planning aims to lay down the strategic directions that the company will follow in the medium and long term. This is not very detailed. Strategic planning deals with trends rather than details.

7. 	Corporate planning - making the strategic choices (long-term), affirming the commitment to undertake corporate restructuring. It includes a decision which of the current SBUs to drop (divest), which ones to develop further, and which new ones to start with. These decisions are obviously based on the internal strengths, external opportunities, and corporate objectives identified before. They include an assessment of the ‘attractiveness of the market’ on the one hand and ‘the ability of the company to compete successfully on that market’ on the other hand. The strategic choices to be made set priorities for possible investment decisions at the corporate and SBU levels, and require an analysis of their financial and operational feasibility.

8.	Tactical planning (medium term) for each of the selected SBUs. Whether to produce sausages or bread is a strategic decision, based on the SWOT and conclusions of the diagnostic. How to market them is a tactical decision: in marketing planning we work out in detail how the strategic objectives that are related to the commercialisation of the products will be reached. This plan indicates specific actions to be undertaken. Likewise, production, organisation / HRM, and financial management plans are developed.

9. 	Financial implications: revenue projections / cash flow planning, projected profit & loss statements and projected balance sheets of the restructuring plan. If so needed, several scenario’s may be developed reflecting variations in uncertain and difficult to predict factors.

10. 	Monitoring & control: mile stone path. In order to concretise the restructuring effort, an action plan is developed, indicating who will be responsible for the respective actions to be undertaken in the implementation of the strategic plan, and when these actions will be undertaken.

The restructuring plan should probably be approved and adopted by the board of directors or meeting of shareholders. In case of liquidation or bankruptcy, the plan is approved by the bankruptcy court. To facilitate the process, the restructuring plan should be written in a logical and easy accessible manner. The table of contents of the restructuring plan is graphically shown in annex E. In annex F a model to summarise the restructuring plan is shown. Using this template, the entire restructuring plan can be presented in no more than three pages.

# IV	Implementation

During the implementation of the restructuring plan, the action plan plays a key role. As this plan indicates what is to be done, when and by whom, it guides day-to-day actions of management. The plan is adapted regularly as the market conditions change. However, the global objectives and strategies should not normally be changed, unless there is really a significant shift in the company’s external and internal environment. Changes in company strategy probably require a decision of the board of directors or shareholders.

It is noted that apart from the above mentioned strategic and tactical planning, the company will also engage in some micro planning at the department and even personnel level. The action plan forms the basis for the subsequent development of department plans, and eventually personal performance and development plans.

# Annex A - Overview of the Restructuring Process

|  |  | Internal analysis of marketing, production, organisation and finance functions. Analysis of business units |  | External analysis – market, competitive, economic and legal environment |
| --- | --- | --- | --- | --- |
| Diagnostic |  |  |  |  |
|  |  |  | SWOT at the strategic level – Identify the competitive advantages |  |
|  |  |  | Strategic planning: definition of corporate objectives, mission statement, and corporate (business unit) strategy |  |
| Planning |  |  |  |  |
|  |  |  | Tactical planning: marketing, production, organisation and finance objectives and strategies |  |
| Implementation |  |  | Action plan, to put actions in a time frame, assign responsibilities, and monitor progress |  |

# Annex B - Ten steps in Diagnostic and Planning

Annex C - Diagnostic tables, example

| Problems observed | Consequences | Solutions |
| --- | --- | --- |
| Marketing |  |  |
| Clients do not trust local products, prefer imported ones | No sales, loss of market to imports | Produce foreign products under license |
| …. |  |  |
| Production |  |  |
| All installations and buildings are greatly over-dimensioned to current and expected needs | High energy, maintenance and depreciation expenses | Down-scaling of existing facilities. If replacement is considered, lower but more flexible capacities |
| …. |  |  |
| Organisation / HRM |  |  |
| Company structure is production and technology orientated, with excessive vertical integration (all support functions in house) | Company is not market orientated / organised. Many support units not feasible to keep ‘in-house’. The same for by-products | Profit centre approach, lease out or sell unprofitable support units, buy outside support if cheaper, divest some by-product units |
| …. |  |  |
| Finance |  |  |
| No provision of accurate and timely financial information to management | Management can not make well-informed decisions | Monthly management accounts |
| …. |  |  |

Annex D - SWOT

| Strengths : what we do well Improve… Close to international airport | Weaknesses : what we do not do well Poor marketing know how and practice Food safety and packaging standards do not satisfy ‘advanced’ export markets |
| --- | --- |
| Opportunities : external factors favourable to us Take Advantage… Likelihood of export markets in Middle East | Threats : external factors working against us Upgrade… Hygienic standards on export markets are increased, approaching EU standards |

# Annex E - Strategic Planning Framework – Contents of the restructuring plan

|  |  | Analysis of external, customer, and internal environments (company diagnostic) (Annex A) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | SWOT analysis at the strategic level: analysis of internal strengths and weaknesses, and external opportunities and threats (Chapter two) |  |  |  |  |
|  |  | Development of mission statement and corporate objectives (Chapter three) |  |  |  |  |
|  |  | Formulation of Corporate or Business Unit Strategy (Chapter four) |  |  |  |  |
| Marketing - Objectives - Strategy - Implementation and resources needed (Chapter five) |  | Production - Objectives - Strategy - Implementation and resources needed (Chapter six) |  | Organisation / Human resources - Objectives - Strategy - Implementation and resources needed (Chapter seven) |  | Financial management - Objectives - Strategy - Implementation and resources needed (Chapter eight) |
|  |  | Financial Projections (chapter nine) Action Plan 2000 (and annual updates) (Chapter ten) |  |  |  |  |

# Annex F – Strategic Planning Matrix – Summary of the restructuring plan

| Mission statement: |  |  |  |
| --- | --- | --- | --- |
| Restructuring Goal (medium and long-term): |  |  |  |
| Corporate Objectives (short and medium term): 1… 2… 3… |  | Corporate Strategy: |  |
| Marketing objectives: 1… 2… 3… | Production objectives: 1… 2… 3… | Organisation / HRM objectives: 1… 2… 3… | Finance objectives: 1… 2… 3… |
| Marketing strategy: 1.1… 1.2… 1.3… 2.1… 2.2… 2.3… 3.1… 3.2… | Production strategy: 1.1… 1.2… 1.3… 2.1… 2.2… 2.3… 3.1… 3.2… | Organisation / HRM strategy: 1.1… 1.2… 1.3… 2.1… 2.2… 2.3… 3.1… 3.2… | Finance strategy: 1.1… 1.2… 1.3… 2.1… 2.2… 2.3… 3.1… 3.2… |
| Resources needed: 1… 2… 3… | Resources needed: 1… 2… 3… | Resources needed: 1… 2… 3… | Resources needed: 1… 2… 3… |